Progress to date:

| Stage 1 Nov 2025 – Feb 2026 | Establishment: Designating area and formally submitting application, setting up a steering group and establishing local interest. | November 2025: -Steering group created. -Neighbourhood Area for NDP designated. -Public information and interest meeting held. -Social media used to raise awareness. December 2025: -Website established. February 2026: -Steering group meeting with Laila Bassett (West Berks Planning officer). |
| --- | --- | --- |
| Stage 2 March 2026– April 2026 | Engagement: Raising awareness, gathering and analysing local priorities to inform direction of plan. | March 2026: -Questionnaire developed and delivered to all houses in the Parish. -Door to door discussions to raise awareness. -Social media, village notice boards and village magazine used to gain awareness and update parishioners on progress. April 2026: -Analysis of questionnaires by steering group |

Next steps:

| Stage 3 Estimated: May 2026-Feb 2027 | Documentation: Gathering and analysing evidence, producing draft policies and plan. | Exp. June 2026 onwards: -Researching and gathering Midgham specific data. -Initial drafting of policies. -Gaining feedback from local community for these. |
| --- | --- | --- |
| Stage 4 Estimated: Feb 2027 onwards | Finalising Policies and Plan: Submission, final consultation, and referendum. | Exp. Feb 2027 onwards : -Consultation. -Submission. -Independent examination. -Referendum. |

Actions in white italics are included to give an indication of next steps and time frames. They are subject to change.