Midgham Neighbourhood Development Plan

Seventh Planning Meeting on Midgham Neighbourhood Development Plan (NDP).

Date: 22nd July 2026

Time: 18.00-20.00

Location: Berkshire Arms

Meeting type: NDP Steering Group – Planning Meeting

Attendees

- Anthony Fenn - Chair, Midgham Parish Council

- Caroline Tocher – Local parishioner, NDP Steering Group member

- Dawn Adams – Parish Councillor, Midgham Parish Council

- Sue Ellis – Local heritage expert, NDP Steering Group member

- Chris Read – District Councillor; Secretary, Midgham NDP Steering Group

Apologies

- Louisa Lai – NDP Steering Group member

- Nigel Bassford – Parish Councillor

Objective of meeting

- Review the Vision for the NDP.

- Discuss spatial strategy provided in the template provided by our consultant.

- Update on policies already begun

- Review the task list and assign policies to members to start evidencing/writing.

- Vision

The following guiding principles agreed upon:

- Keeping Midgham distinct from Thatcham and Woolhampton.

- Maintaining the character of Midgham as an inherently rural Parish with small, scattered communities.

- Ensuring development maintains and strengthens local ecology and character.

- Spatial Strategy

- Discussion of what the spatial strategy should constitute.

- Identifying that the statement ‘encouraging small-scale developments’ is vague and may lead to encouraging development that would otherwise not be allowed.

- Action: Agreed that CT and DA will email consultant for clarity and recommendations for appropriate development styles in different parts of Midgham.

- Discussion around individual policies

Midgham Marsh

- Ecology report to be commissioned to look at bio diversity.

Heritage

- SE updated on progress with the Heritage policy.

- We discussed using heritage to identify the unique identity of the Parish.

Solar Farms

- Agreed that commercial solar farms were unlikely to be in keeping with the NDP Vision, or welcomed by the community.

- Action: Agreed that CT and DA would email consultant to clarify whether a specific policy was helpful.

- Review of the Task List

- Each point was looked at in turn and the following tasks were assigned to individual members to lead on:

- 3 Proof reading: AF

- 10 Vision and objectives workshop: CT

- 15-16 Pen portrait and census data: CT and SE

- 17 Issues and opportunities: CR

- 18-19 Vision and objectives: CT

- 23 Character and Design: SE

- 25: Renewable and community-scale energy: CR

- 26: Conserving heritage assets: SE

- 27: Natural environment and biodiversity: AF

- 28: Local Green spaces: CT

- 29: Locally significant views: NB

- 30: Dark skies: NB and DA

Next Meeting

To be agreed for August. A public engagement session is loosely planned for October and planning for this would be key for the next few meetings.

Actions Log

No. 	Action				Responsible	Deadline

1	Email consultant for clarity	CT and DA	ASAP

on spatial strategy and

solar farms.